## Algorithm Tracker
Algorithm Name (5.0) | # of consecutice days to run alert, Apollo needs to start at current date | Design Review | 1st Pass in Apollo | Parameter settings Charting (2nd Pass) QlikView Dashboards and Charts | 3rd Pass (Data Issue or Analysis needed) | Run in Apollo with Current data | Spec Sheet | Open Issues
PHN Alinity i Optics Dark Counts for Apollo | 1 | 2019-08-14 | Runs Successfully in Apollo 5.0 |  | Data needs to be reviewed IDA vs DX (check Suppression list) |  | Drafted
PHN Alinity i Pipettor FE Pressure for Apollo | 1 | 2019-08-15 | Runs Successfully in Apollo 5.0 |  | Data needs to be reviewed IDA vs DX (check Suppression list) |  | Drafted
PHN Alinity i Vacuum Sensor for Apollo | 1 | 2019-08-20 | Runs Successfully in Apollo 5.0 |  | Data matched , checked by Jun. |  | Drafted
PHN Alinity i Pipettor Syringe Backlash for Apollo | 1 | 2019-08-21 | Runs Successfully in Apollo 5.0 |  | Data matched , checked by Jun. |  | Drafted
PHN Alinity i Washzone Aspiration for Apollo | 1 | 2019-08-22 | Runs Successfully in Apollo 5.0 |  | Data needs to be reviewed IDA vs DX (check Suppression list) |  | Drafted
PHN Alinity i Vacuum Leak for Apollo | 7 | 2019-08-26 | Runs Successfully in Apollo 5.0 |  | Data needs to be reviewed IDA vs DX (check Suppression list) |  | Drafted
PHN Alinity i Vacuum Pump for Apollo | 1 | 2019-08-27 | Runs Successfully in Apollo 5.0 |  | Data needs to be reviewed IDA vs DX (check Suppression list) |  | Drafted
PHN Alinity Cuvette Wash | 7 | 2019-08-27 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Alinity Cuvette Integrity | 7 | 2019-08-28 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Alinity HC Waste | 60 | 2019-09-30 | Need to be deployed in Apollo 5.0
PHN Alinity Waterbath Optical Interference | 1 | 2019-09-30 | Need to be deployed in Apollo 5.0
PHN Alinity IA Process Path Jams 5756 | 1 | 2019-09-17 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Alinity IA Process Path Jams 5758 | 1 | 2019-09-17 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Alinity ITV | 1 | 2019-10-08 | Need to be deployed in Apollo 5.0
PHN Alinity RSM Pick and Place | 7 | 10/11/2019 - Remediation done - WDC added - MAR Needs code remediation Need to add reliability check for install to close to 60 days WDC=11000 EXP Code=1100
PHN Alinity Trigger/Pretriger Dispense | 1 | 10/11/2019 - Remediation done - MAR
PHN Architect Dark Count > 250 | 1 | 2019-08-28 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Architect SD > 100 | 1 | 2019-08-28 | Runs Successfully in Apollo 5.0
PHN Architect FE Pressure | 1 | 2019-08-28 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Architect WAM Pattern A | 1 | 2019-09-06 | Runs Successfully in Apollo 5.0 |  |  |  | Drafted
PHN Architect WAM Pattern B | 1 | 2019-09-06 | Code has changed, needs to be re-run in Apollo 5.0 |  |  |  | pending
PHN Architect WAM Pattern C | 1 | ON HOLD | on HOLD |  |  |  | Drafted
CC Cuvette LLS Board, CC Cuvette Status Check - Broken Cuvette, CC Cuvette Wash Subassembly | 7 | 2019-09-12 | Ran in Apollo 5.0
DM Fail CC | 1 | Needs code remediation
DM Fail IA | 1 | Needs code remediation
Architect HC Waste Algorithm | 60
A3600 | 30 | 2019-09-09 | Sent to Siva (Draft copy) to run
APS | 30 | 2019-10-09 | Draft Reviewed
Architect PdM | 31

## Issue Tracker
Algorithm Name (5.0) | Open Issue | Reported By | Date Open | Date Resolved | Testing by Apollo Team
WAM | Charting changes as described by Siva | Siva | 2019-09-12 | 2019-09-13
WAM | Level 3 DESC | Siva | 2019-09-12 | 2019-09-13
A3600 | Date Format Issse | Siva | 2019-09-16 | 2019-09-17 | 2019-09-17
A3600 | Flag not dispalyed as 1/0 in results.csv | Siva | 2019-09-16 | 2019-09-18 | 2019-09-18
A3600 | PL displayed is incorrect | Siva | 2019-09-16 | 2019-09-18
Achitect Cuvette | Date Format Issue | Siva | 2019-09-17 | 2019-09-19 | 2019-09-19
Architect cuvette | Healthy Instruments are not there | Siva | 2019-09-17 | 2019-09-19
Architect cuvette | Only one type of Algorithm desc in results file | Siva | 2019-09-17 | 2019-09-19
Spec Sheets - All | How is TOR set for all Alinity Algorithms? And Update Spec sheets accordingly | Deborah | 2019-10-09
Data Delay Issue | Investigate data delay issues | Nate/Deborah | 2019-10-09
R query Documentation | Document all R queries (R sql query only) | Deborah | 2019-10-09
Spark Algorithm | Compare performance for existing Algorithm using SPARK | Deborah | 2019-10-09