## Status
PHN Alert | Developed By | Platform | Type | Algorithm Review Date | Comments from Review | Design Doc | Manual Monitoring | ODS completed | Spec Sheet Status | Coding in Apollo | Verified in Apollo | APLM Spec Sheet | TCT Code | KM Article Number | ISA Release | Apollo Suppression Exp Codes | Applicable WDC | Part Replaced | Launched to the field | Design Changes
Trigger/Pre-trigger Dispense | QE | IA | Data Threshold | 2018-09-20 | Call Center | D000072998 | 2019-04-18 | Yes | Sent to jun 6/14 | 2019-07-03 | Jun Unit test in production Need to use Toad. All matched 7-15 | Jun to update | CCN1 | K66203158 |  | C9F1, C9F2, C9L1, C9L2, B8FA, B8LA, CBF2, CBF1, CBF3, CBF4, CBF5, CBL2, CBL1, CBL3, CBL4, CBL5 | CE*, CD*, CS* | LN 04S68
RSM Pick and Load | QE | ci | Data Threshold | 2018-08-09 | Needs to be for Call Center first | D000059484 | 2019-04-18 | Yes | Drafted | 2019-07-03 | Jun Unit test in production Need to use Toad. All matched 7-15 | Jun to update | A832 | K91150585 |  | A4Z5, A4Z1, A4Z2, A4Z6, A4ZG, A4Z7, A4Z3, A4Z8, A4ZH, A4Z9, A4ZA, A4Z4 | DA** Transport, Robotics, Waste Disposal & Other Hardware; RSM Transport (Theta and Z Axis)
HC Waste Pump Tubing | GSS | CC | Signal Threshold | 2019-06-06 |  | N/A | N/A | Yes | Drafted- Cory input | 2019-07-03 | New ODS |  | B912 | K34464264 |  | ACVS, DFV(1,Z,3,K,5,6,H,S), DFW(Z,5,6,T,1,S) | C5**, CH**, C3**, B2**
Waterbath Optical Interference | GSS | CC | Signal Threshold | 2019-06-06 |  | N/A | N/A | Yes | Drafted- Cory input | 2019-07-03 | New ODS |  | B941 | K14312423 |  | FAA1, FAAF, FAA2,B2M2 | FAG*, CWF*, CWG* ,CC*
Daily Maintenance | GSS | IA | Data Threshold | 2019-06-06 |  | N/A | 2019-05-28 |  | Drafted- Cory input | 2019-07-02 | Cory completed | Complete 7-15 | CCK1 | K90121242 |  | N/A | N/A
Daily Maintenance | GSS | CC | Data Threshold | 2019-06-06 |  | N/A | 2019-05-28 |  | Drafted- Cory input | 2019-07-02 | Cory completed | Complete 7-15 | B9K1 | K55944704 |  | N/A | N/A
Weekly Maintenance | GSS | IA | [10 empty] | CCK2
Weekly Maintenance | GSS | CC | [10 empty] | B9K2
RSM Movement | QE | ci | Data Threshold | 2017-11-02 | ON HOLD PRS Open | D000047937 | 2018-03-23 | [5 empty] | A831 | [6 empty] | Carrier Transport, S/W 2.1
Washzone Heater | QE | IA | Data Threshold | 2017-10-26 | ON HOLD, PRS OPENED Needs to be re-evaluated for using ambient temperature |  | 2018-02-26 | [5 empty] | CC77 (WZ1) CC87 (WZ2) | K24157724 |  | C51 (Z,C,A,B,E) C5T (Z,C,A,B,E) | E13* Temperature; Buffer Heater – WZ1; Erratic / Unstable Temperature E15* Temperature; Buffer Heater – WZ1; Temp Too Low E16* Temperature; Buffer Heater – WZ1; Temp Too High E23* Temperature; Buffer Heater – WZ2; Erratic / Unstable Temperature E25* Temperature; Buffer Heater – WZ2; Temp Too Low E26* Temperature; Buffer Heater – WZ2; Temp Too High
RV Loader Movement | QE | IA | Message Threshold | 2017-05-18 | Go |  | 2017-06-06 | Yes | Updates for Apollo |  |  |  | CCQ2 | K57988564 | ISA-205-016A |  |  |  | 12/17/2017 Manual EMEA | RSM Improvement in S/W 2.1 RV Picker Finger
Waterbath Fill Time | GSS | CC | Data Threshold |  | In GSS development
AbbottLink Low Disk Space | GSS | IA&CC
Dispersion | GSS | IA | Data Threshold |  | In GSS development | [14 empty] | Dispersion Post Alignment (TSB-004) Gear change (Dust)
Vacuum Restriction | QE | IA | Data Threshold
Reagent Carousel Torque | GSS | IA | [17 empty] | Dust due to pulley key wear
CABS Gear Pump | GSS | CC
CI Coolant Expiration | GSS | IA&CC

## Launched
PHN Alert | Developed By | Platform | Type | Algorithm Review Date | Comments from Review | Design Doc | Manual Monitoring | Spec Sheet Status | TCT Code | KM Article Number | ISA Release | Apollo Suppression Exp Codes | Applicable WDC | Part Replaced | Launched to the field | Design Changes | Apollo ODS | Apollo Algorithm Coding | Apollo Parameters In Control Panel | Verification (Before move to Production) | Deposit Spec Sheet in APLM | Moved to Production | Countries Enabled
Dark Counts | QE | IA | Data Threshold | 2017-03-27 | Go |  | 2017-04-26 | Moved to Apollo Coding | CCA1 | K07342335 | ISA-205-016A | Z1OP, Z1OR, FAAA, FAAB, FAA1, FAC1 | FA3*: Optics CMIA Background/ Stray light FAG*: Optics CMIA Debris/dirty FB3*: Optics Reader Shutter Background FBG*: Optics Reader Shutter Dirty |  | 12/17/2017 Manual EMEA WW July 2, 2018 | Shutter Pin (Q2) | In Dev Environment | Code Under Test in Dev April 1 | Completed in Dev | 2018-05-25 |  | 2018-07-01
FE Pressure | QE | IA | Data Threshold | 2017-02-28 | Go |  | 2017-04-26 | Moved to Apollo Coding | CC11,CC21,CCJ1 | K82525012 | ISA-205-016A | None | R1: BB1* Fluid Aspiration, Dispense and Detection, R2: BC1*: Fluid Aspiration, Dispense and Detection, Sample: B31*: Fluid Aspiration, Dispense and Detection | 7-204217-02 | 12/17/2017 Manual EMEA WW July 2, 2018 |  | In Dev Environment | Code Under Test in Dev April 1 | Completed in Dev | 2018-05-25 |  | 2018-07-01
Vacuum Sensor | QE | IA | Data Threshold | 2017-05-16 | On Hold Multi Module Instrument misidentified in PABBTO (Fix in SW 2) Needs Level 3 TCT in Apollo |  | 2017-05-16 | Moved to Apollo Coding | CCE3 | K51814801 | ISA-205-016A | None | CW* Fluid Movement, Vacuum Failure | A-30104916-01 | 12/17/2017 Manual EMEA WW July 2, 2018 |  | In Dev Environment | Code Under Test in Dev 4/23/18 | Completed in Dev | 2018-05-25 |  | 2018-07-01
Process Path Retries (5756) | QE | IA | Aim Code | 2017-05-11 | On Hold. No subcodes in error code for path identification Possible data table disconnect (Message History and Instrument Activity Data shows < 24 hours warning Subcodes verified by GSS in S/W 1.2 |  | 2017-07-18 | Moved to Apollo Coding | CCG1 (PP) CCl1 (Pretreat) | KM1158157 | ISA-205-016A | Z75L, Z75P, Z75Q, A3G1, A3G7, B5G7 | DFL*: Transport, Robotics, Waste Disposal & Other Hardware, Process Path, Jams DFG*: Transport, Robotics, Waste Disposal & Other Hardware, Process Path, Buildup of Debris or Dirty | Should WDC be 2 digitsTicket has DFE | 12/17/2017 Manual EMEA WW July 2, 2018 | Upgrade to double stack motor (Q2) | In Dev Environment | Completed in Dev | Completed in Dev | 2018-06-19 |  | 2018-07-01
Process Path Retries (5758) | QE | IA | Aim Code | 2017-05-11 | Subcodes verified by GSS in S/W 1.2 |  | 2017-07-18 | Moved to Apollo Coding | CCG1 (PP) CCl1 (Pretreat) | KM1158157 | ISA-205-016A | Z75L, Z75P, Z75Q, A3G1, A3G7, B5G7 | DFL*: Transport, Robotics, Waste Disposal & Other Hardware, Process Path, Jams DFG*: Transport, Robotics, Waste Disposal & Other Hardware, Process Path, Buildup of Debris or Dirty |  | 12/17/2017 Manual EMEA WW July 2, 2018 | Upgrade to double stack motor (Q2) | In Dev Environment | Completed in Dev | Completed in Dev | 2018-06-19 |  | 2018-07-01
ITV PWM | GSS | IA | Data Threshold | 2016-10-26 | In GSS Monitoring |  | 2017-09-18 | Moved to Apollo Coding | CC31,CC41,CC51,CC61 | K04134211 | ISA-205-016A | See Codes Tab | C8**: Fluid Movement:Vortexer VTXR1 C9**: Fluid Movement:Vortexer VTXR2 CJ**: Fluid Movement:Vortexer VTXR4 CI**: Fluid Movement:Vortexer VTRX3 |  | 12/17/2017 Manual EMEA WW July 2, 2018 | End of Life hardware and S/W changes | In Dev Environment | Code Under Test in Dev | Completed in Dev | 2018-06-19 |  | 2018-07-01
Syringe Backlash | QE | IA | Data Threshold | 2017-10-04 | In GSS Monitoring |  | 2017-11-01 | Moved to Apollo Coding | CC12 (R1) CC22 (R2) CCJ2 (s) | K09702532 | ISA-205-016B | None | CB** Fluid Movement, R1 Syringe CC** Fluid Movement, R2 Syringe CA** Fluid Movement, Sample Syringe | 7-77650-05 | 2018-07-02 | Syringe Failure, new part Part 7-7765-05 Replace on failure | In Dev Environment | Code Under Test in Dev | Completed in Dev | 2018-06-19 |  | 2018-07-01
Washzone Aspiration | QE | IA | Data Threshold | 2017-10-26 | In GSS Monitoring |  | 2017-11-01 | Moved to Apollo Coding | CC74 (WZ1, P1) CC75 (WZ1, P2) CC76 (WZ1, P3) CC84 (WZ2, P1) CC85 (WZ2, P2) CC86 (WZ2, P3) | K27928144 | ISA-205-016B | ABT3, ABT5, AB13, AB15 B71B, B712, B7TB, B7T2 A2T2, A2T3, A212, A213 | BJ3* - Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Aspiration Error / WAM BJH* - Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Clog / Clot / Obstruction BJM* - Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Leaks / Drips B73* - Fluid Aspiration, Dispense and Detection; Wash Zone2 Probe; Aspiration Error / WAM; Aligned / Adjusted / Calibrated B7H* - Fluid Aspiration, Dispense and Detection; Wash Zone 2 Probe; Clog / Clot / Obstruction B7M* - Fluid Aspiration, Dispense and Detection; Wash Zone2 Probe; Leaks / Drips | NEED TO UPDATE AND GO 2 DIGITS: | 2018-07-02 | Tubing/Oriface widening. TSB-205-013 | In Dev Environment | Code Under Test in Dev | Completed in Dev | 2018-06-19 |  | 2018-07-01
Vacuum System Leak | QE | IA | Data Threshold | 2018-05-10 | Troubleshoot Vacuum Assembly |  | 2018-06-18 | Moved to Apollo Coding June 15 | CCE1 | K70550866 | ISA-205-016c | AA3Z | D3V*: Transport, Robotics, Waste Disposal & Other Hardware: Waste Accumulator:Vacuum System Issue/Failure A1V*: Transport, Robotics, Waste Disposal & Other Hardware: Waste Accumulator:Vacuum System Issue/Failure |  | 2018-08-13 |  | In Dev Environment | 2018-06-25 | 2018-06-25 | 2018-07-03 |  | 2018-07-25
Vacuum Pump | QE | IA | Data Threshold | 2018-05-31 | Repair the pump heads or replace pumps if necessary |  | 2018-06-18 | Moved to Apollo Coding June 15 | CCE2 | K72294393 | ISA-205-016C | Z3OI | CWC*: Fluid Movement: Vacuum failure: Other | A-30111940-02 | 2018-08-13 | A-30111940-1 Pump repair kit | In Dev Environment | 2018-06-20 | 2018-06-20 | 2018-06-24 |  | 2018-07-25
AbbottLink Disconnect | GSS | IA&CC | Data Threshold | 2018-05-09 | Needs Apollo 4.0 update to grab data |  |  | Moved to Apollo Coding | A81Z | K83792240 | ISA-205-016B | SACA, SACC, SACE, SA3A, SA3C, SA3D | LA** A/L Communication LBE* A/L Configuration Application S/W L1** A/L Network LD** A/L Lockup |  | 2018-07-02 |  | In Dev Environment | 2018-06-29 | 2018-06-29 | 2018-06-29 |  | 2018-06-29
Cuvette Integrity | GSS | CC | Data Threshold |  |  |  | 2018-03-23 |  | B972(1), B973(2), B974(3), B975(4), B976(5), B978(6), B979(7), B97A(8), B97B(9), B97C(10), B97D(11), B97E(12), B97F(13), B97G(14), B97H(15), B97I(16), B97J(17) | K31460679 |  | Z5O0: 4703 Cuvette integrity check failed on cuvette (0). FA7K: Optice/Detector, Cuvette Damaged/Cracked/Scratched Z3UO: 3423 Cuvette washer water volume (0). Cuvette (1) volume (2). | F7** Optics/Detecter Cuvette |  | 2018-11-19
Cuvette Wash | GSS | CC | Data Threshold |  |  |  | 2018-03-23 |  | B97K | K41225806 |  | BJT (Z,3,6,D,4,5,7,1,H,9,U,S) BJ1Z, BJ4(Z,6,H,9,U) A31 (Z,7,1) Z60O: 4703 Cuvette integrity check failed on cuvette (0). Z61H: 5112 Cuvette washer lower limit not found. Z73E: 5651 Cuvette washer movement restricted at position (0) step number (1). Z3UO: 3423 Cuvette washer water volume (0). Cuvette (1) volume (2). | CJ** Fluid Movement Cuvette Wash Pump CT** Fluid Movement Cuvette Wash Pump Valve BP** Fluid Aspiration, Dispense and Detection Cuvette Washer F7** Optics/Detecter Cuvette |  | 2018-11-19

## Contract Numbers
01DP4-01 | ALNTY C SVC CONTR PKG A | Enabled for PHM Use | NDR
01DP4-02 | ALNTY C SVC CONTR PKG A | Enabled for PHM Use | SDR
01DP4-03 | ALNTY C SVC CONTR PKG A | Enabled for PHM Use | AOS 3
01DP4-09 | ALNTY C SVC CONTR PKG A |  | 2DR
01DP4-80 | ALNTY C OTH CST CARE RA | Enabled for PHM Use | RAP-Dist
01DP4-83 | ALNTY C OTH CUST CARE R | Enabled for PHM Use | RAP/CPR
01DP4-84 | ALNTY C OTH CST CARE RA | Enabled for PHM Use | RAP-AOS2
01DP4-89 | ALNTY C OTH CST CARE RA | Enabled for PHM Use | RAP-AOS3
01DP5-01 | ALNTY I SVC CONTR PKG A | Enabled for PHM Use | NDR
01DP5-02 | ALNTY I SVC CONTR PKG A | Enabled for PHM Use | SDR
01DP5-03 | ALNTY I SVC CONTR PKG A | Enabled for PHM Use | AOS 3
01DP5-09 | ALNTY I SVC CONTR PKG A |  | 2DR
01DP5-80 | ALNTY I OTH CST CARE RA | Enabled for PHM Use | RAP-Dist
01DP5-83 | ALNTY I OTH CUST CARE R | Enabled for PHM Use | RAP/CPR
01DP5-84 | ALNTY I OTH CST CARE RA | Enabled for PHM Use | RAP-AOS2
01DP5-89 | ALNTY I OTH CST CARE RA | Enabled for PHM Use | RAP-AOS3
01DP6-01 | ALNTY SCM SVC CONTR PKG | Enabled for PHM Use | NDR
01DP6-02 | ALNTY SCM SVC CONTR PKG | Enabled for PHM Use | SDR
01DP6-03 | ALNTY SCM SVC CONTR PKG | Enabled for PHM Use | AOS 3
01DP6-09 | ALNTY SCM SVC CONTR PKG |  | 2DR
01DP6-80 | ALNTY SCM CST CARE RAP- | Enabled for PHM Use | RAP-Dist
01DP6-83 | ALNTY SCM OTH CUST CR R | Enabled for PHM Use | RAP/CPR
01DP6-84 | ALNTY SCM CST CARE RAP- | Enabled for PHM Use | RAP-AOS2
01DP6-89 | ALNTY SCM CST CARE RAP- | Enabled for PHM Use | RAP-AOS3

## codes
Alinity PHN Name | Arch EC | Arch Text | Alinity Experience Codes | Alinity Text | TCT WDC | WDC Text | Ticket WDC | Ticket WDC | Ticket WDC
Dark Counts | CCFD (FN) | Fluidics Issues Valves Pretrigger Debris, Leaks Drips | N/A
| CCLD (LN) | Fluidics Issues Valves Pretrigger Debris, Leaks Drips | N/A
| Z0R6 | 1005 Result cannot be calculated RLU read out | N/A
| Z0RA | 1007, activated read failure | N/A
| Z0R8 | 1006 Unable to process test Background | Z1OP | 1401 Unable to process test. Background read failure. |  |  | None
| Z0RC | 1008 final read failure | Z1OR | Z1OR: 1403 Unable to process test. Final read failure. |  |  | None
| FAAA |  | FAAA | Optics,CMIA, Background stray light |  |  | 19100 Customer Care
| FAAG |  | FAAB | Optics, CMIA, other read errors |  |  | FA6IG (Low Read) Straw replaced | FA3IG (AI01086)
| FAAB |  | FAA1 | Optics, CMIA, Dirty |  |  | BD9SG (sample Pipettor)
| FACB |  | FAC1 | Optics, Shutter, Dirty
AbbottLink Disconnect | A131 | A/L Network, Abbott Network | SACA | A/L Network, Abbott Network |  |  | NONE
| A132 | A/L Network, Customer Netwk | SACC | A/L Network, Customer Netwk |  |  | L1BZA,CNBD Phone | LAEZJ, LBEZG. Application S/W
| A133 | A/L network, LAN Jack, cable | SACE | A/L network, LAN Jack, cable |  |  | none
| A151 | A/L, S/W/ Comm | SA3A | A/L, S/W/ Comm |  |  | None
| A153 | A/L, S/W, Data Exchange | SA3C | A/L, S/W, Data Exchange |  |  | LAEZZ. LBEZZ, LBEZL ApplS/W CNBD
| A154 | A/L, S/W Disconnected/Miss | SA3D | A/L, S/W Disconnected/Miss |  |  | LAEEG Appl S/W reinstall
|  |  | SA1 | A/L Firewall |  |  | 5 Tickets
FE Pressure | A811 | PdM Pipettor Dispense | N/A
| A823 | PdM FLMD MV syringe | N/A
| Z1RM | 3350 Unable to process test, aspiration error for (R1 Pipettor) at (Reagent Carousel). | N/A
| Z1RN | 3350 Unable to process test, aspiration error for (R1 Pipettor) at (RV2). | N/A
| Z1RP | 3350 Unable to process test, aspiration error for (R1 Pipettor) at (Wash Station). | N/A
| Z1S3 | 3353 Aspiration error on liquid level sense board (1), pressure discord score. (R1 Pipettor at wash station) | N/A
| Z1SA | 3355 Aspiration error on liquid level sense board (x), incomplete aspiration. | N/A
|  |  | Z3O6 | 3203 Pressure monitoring error on ({0}) pipettor at location ({5}) carousel position ({3}).
|  |  | Z305 | 3202 Pressure monitoring error on (0) pipettor during wash.
|  |  | Z309 | 3215 Pressure monitoring error for (0) pipettor in (5).
|  |  | Z4OC | 3461 Unable to process test. Pressure monitoring error detected during the sample aspiration.
| A9I1 | PHN EC3350 RV Carousel | N/A
| A9H1 | PHN EC3350 Reagent | N/A
Vacuum Sensor | N/A |  | Z3OC | 3304 ICQ System Vacuum Failure (Vacuum pressure too high).
|  |  | Z3OB | 3303 Vacuum system failed. Vacuum sensor base too low.
|  |  | Z3OD | 3305 Vacuum system failed. Vacuum pressure error.
|  |  | Z3OH | 3309 Vacuum system pressure error.
PROCESS PATH | Z2GQ | 5106 A process path recovery was successfully performed
|  |  | N/A | 5756: Process path jam recovery on (0) successful. STATUS Message
|  |  | Z75L | 5752 Process path move error on (0) lane
|  |  | Z75P | 5757 Process path jam recoveries on (0) excessive.
|  |  | Z75Q | 5758 Process path jam recovery successful on (0). Process path may require servicing.
| A852 | PHN | N/A
| A671 | PHN | N/A
| A971 | PHN | N/A
| DBJ | Carousels Issue, Process path, | A3G | Process Path Issue, Process Path
| DBJA | Buildup of Debris or Dirty
| DBJF | Homing Error | *E | Homing/Step Loss/ Motor Command
| DBJG | Jams | A3G1 | Jam/Stuck | DF | Transport, Robotics, Waste Disposal & Other Hardware, Process Path, | DFLTG:Transport, Robotics, Waste Disposal & Other Hardware, Process Path, Jams, Cleaned Hardware/Component, FSR - Site Visit
| DBJN | Step Loss | A3G7 | Process Path Issue, Process Path Movement Not as Expected/No Movement | DFL | *, Jams
|  |  | B5G7 | Robotics Issue: Process Path/Supply Center Process Path Movement Not as Expected/No Movement | DFG | * Buildup of Debris or Dirty
DF
Vortexer VTXR1 PWM |  |  | C32K | Fluidics Issue: Vortexer VTXR1 Step Loss/Stalls/Speed/Cycle Errors | C8 | Fluid Movement:Vortexer VTXR1
|  |  | C327 | Fluidics Issue: Vortexer VTXR1 Movement not as expeted
|  |  | C321 | Fluidics Issue: Vortexer Vortexer VTXR1 Vortex Errors (Engage/Disengage/Time)
|  |  | A6NK | Votexer Issue: Vortexer #1 Step Loss/Stalls/Speed/Cycle Errors
|  |  | A6N1 | Votexer Issue: Vortexer #1 Vortex Errors (Engage/Disengage/Time)
|  |  | Z6OO | 5309 (R1) vortexer did not reach required speed.
|  |  | Z6OC | 5306 (R1) vortexer did not disengage from RV.
|  |  | Z6OG | 5307 (R1) vortexer did not engage with RV.
|  |  | Z6OK | 5308 (R1) vortexer mixing error.
Vortexer VTXR2 PWM |  |  | C33K | Fluidics Issue: Vortexer VTXR2 Step Loss/Stalls/Speed/Cycle Errors | C9 | Fluid Movement:Vortexer VTXR2
|  |  | C337 | Fluidics Issue: Vortexer VTXR2 Movement not as expeted
|  |  | C331 | Fluidics Issue: Vortexer Vortexer VTXR2 Vortex Errors (Engage/Disengage/Time)
|  |  | A6OK | Votexer Issue: Vortexer #2 Step Loss/Stalls/Speed/Cycle Errors
|  |  | A6O1 | Votexer Issue: Vortexer #2 Vortex Errors (Engage/Disengage/Time)
|  |  | Z6OP | 5309 (R2) vortexer did not reach required speed.
|  |  | Z6OD | 5306 (R2) vortexer did not disengage from RV.
|  |  | Z6OH | 5307 (R2) vortexer did not engage with RV.
|  |  | Z6OL | 5308 (R2) vortexer mixing error.
Vortexer VTXPT PWM |  |  | C35K | Fluidics Issue: Vortexer VTXPT Step Loss/Stalls/Speed/Cycle Errors | CJ | Fluid Movement:Vortexer VTXR4
|  |  | C357 | Fluidics Issue: Vortexer VTXPT Movement not as expeted
|  |  | C351 | Fluidics Issue: Vortexer Vortexer VTXPT Vortex Errors (Engage/Disengage/Time)
|  |  | A62K | Votexer Issue: Pre-Trigger Step Loss/Stalls/Speed/Cycle Errors
|  |  | A621 | Votexer Issue: Pre-Trigger Vortex Errors (Engage/Disengage/Time)
|  |  | Z6OQ | 5309 (pVTX) vortexer did not reach required speed.
|  |  | Z6OF | 5306 (pVTX) vortexer did not disengage from RV.
|  |  | Z6OI | 5307 (pVTX) vortexer did not engage with RV.
|  |  | Z6OM | 5308 (pVTX) vortexer mixing error.
Vortexer pVTX PWM (Pretreatment) |  |  | C34K | Fluidics Issue: Vortexer pVTX Step Loss/Stalls/Speed/Cycle Errors | CI | Fluid Movement:Vortexer VTRX3
|  |  | C347 | Fluidics Issue: Vortexer pVTX Movement not as expeted
|  |  | C341 | Fluidics Issue: Vortexer Vortexer pVTX Vortex Errors (Engage/Disengage/Time)
|  |  | A61K | Votexer Issue: PreTreat: Step Loss/Stalls/Speed/Cycle Errors
|  |  | A611 | Votexer Issue: PreTreat: Vortex Errors (Engage/Disengage/Time)
|  |  | Z6OR | 5309 (Pretreatment) vortexer did not reach required speed.
|  |  | Z6OE | 5306 (Pretreatment) vortexer did not disengage from RV.
|  |  | Z6OJ | 5307 (Pretreatment) vortexer did not engage with RV.
|  |  | Z6ON | 5308 (Pretreatment) vortexer mixing error.
Syringe Backlash R1 |  |  | N/A |  | CB** | Fluid Movement, R1 Syringe
Syringe Backlash R2 |  |  | N/A |  | CC** | Fluid Movement, R2 Syringe
Syringe Backlash Sample |  |  | N/A |  | CA** | Fluid Movement,Sample Syringe
Washzone Aspiration |  |  | ABT3, ABT5, AB13, AB15 B71B, B712, B7TB, B7T2 A2T2, A2T3, A212, A213 |  | BJ3* | Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Aspiration Error / WAM
[5 empty] | BJH* | Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Clog / Clot / Obstruction
[5 empty] | BJM* | Fluid Aspiration, Dispense and Detection; Wash Zone1 Probe; Leaks / Drips
[5 empty] | B73* | Fluid Aspiration, Dispense and Detection; Wash Zone2 Probe; Aspiration Error / WAM; Aligned / Adjusted / Calibrated
[5 empty] | B7H* | Fluid Aspiration, Dispense and Detection; Wash Zone 2 Probe; Clog / Clot / Obstruction
[5 empty] | B7M* | Fluid Aspiration, Dispense and Detection; Wash Zone2 Probe; Leaks / Drips
Vacuum Pump |  |  | AA3Z | Fluidics Issue: Vacuum Failure:Other: cannot be determined further | CWC* | Fluid Movement: Vacuum failure: Other
|  |  | Z3OI | 3310 Vacuum system failed. Waste pump pressure too low. |  |  | CWCIG: Fluid Movement, Vacuum Failure, Vacuum Failure - Other, Replaced Part(s
Vacuum Leak |  |  | AA3Z | Fluidics Issue: Vacuum Failure:Other: cannot be determined further | CWC* | Fluid Movement: Vacuum failure: Other
[5 empty] | D3V* | Transport, Robotics, Waste Disposal & Other Hardware: Waste Accumulator:Vacuum System Issue/Failure
[5 empty] | A1V* | Transport, Robotics, Waste Disposal & Other Hardware: Waste Accumulator:Vacuum System Issue/Failure