## Slide 1: PHM Algorithm Remediation Timelines
Alinity Algorithms
Alinity CI Algorithms need to be tested against DX by 30th June
Alinity CI Algorithms ported and tested in Apollo 5.0 Dev by 31st August (This is dependent on partitioning and bug fixes, tentatively scheduled for June 10th and dependent on release of Apollo 5.0)
Alinity CI Algorithms moved to production by 7th October
Architect Algorithms
All algorithms tested against DX by 15th August (Dependent on validation of database. Tentative schedule is end of June)
Algorithms ported and tested in Apollo 5.0 Dev by 30th September (dependent on Apollo 5.0 Release)
Algorithms moved to production by 7th October

## Slide 2
WIF: PHM
WIF Dependencies: N/A
Scope / Key Objectives
Successfully launch PHM Algorithms in PROD; Go-Live date of 1st Nov, 2019 Project initiated on 1st Apr, 2019
Accomplishments & Decisions Made
Week of 20th May,2019: Partitioning column in Curated Layer for PHM Algorithms (to be released on June 10,2019)
Health Status:
Green Text: Completed
Yellow Text: Monitoring
Red Text: Action Required
Black: Ongoing or In Queue
Responsibilities
BSS (owner / Abbott PM): Deborah Lemonidis Sogeti Team: Sonia Madan and Mike Rumore
Milestones | Plan Start | Plan End | LBE Date | Status
Environments (DEV, QA, UAT, Pre-PROD, PROD) | 1st April, 2019 | 31st Aug,2019 |  | In Progress
DEV & Design End | 15th April,2019 | 15th Aug,2019 |  | In Progress
Dry Run | 16th Aug,2019 | 30th Sept,2019 |  | 
Business readiness - UAT | 16th Aug 2019 | 30th Sept,2019 |  | 
Hypercare | 1st Oct,2019 | 31st Oct,2019 |  | 
Prod Go/No-Go | 25th Oct,2019 |  |  | 
Go-Live | 1st Nov 2019 |  |  | 
Overall | Budget | Res | Schedule | Scope
Issues / Risks for Escalation
Risk/Issues Testing the bug fixes and data issues in DX tables Changes for partitioning columns in DX

## Slide 3: Program Risks and Issues
ID | Type | Description | Mitigation | Status | Assigned to
1 | Risk – High | PHM | Data unavailability in Some of the DX tables for 2018-2019 time frame. | Open | BDAA Team
2 | Issue | PHM | Data Partitioning column needs to be changed for DX tables in curated layer. | Closed | BDAA Team
Complete list of Risks & Issues are available here
Budget Drivers:
Dependencies with any other external System Release/resource constraints can impact it
The median effort estimate were ROM numbers with assumptions; any solution/design/actual effort change can impact it
Any new software/hardware requirement for performance or business needs can impact it
Scope changes from the original URS/Business needs document can impact it

## Slide 4: Action Items and Next Steps
Item | Description | Status | Assigned To | Due Date | LBE